| OUR WORK PLAN | 2021 | 2022 | 2023 | 2024 | 2025+ | Working Group |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Lead | Advisory Committee Members and other Key Resources (preliminary) | Status |
| Inclusion and Community Engagement |  |  |  |  |  | Pillar lead - Municipalities |  |  |
| Establish inclusion/active anti-racism strategy (PRIORITY) |  |  |  |  |  | Municipalities | Solicitor General - Anti-Racism Directorate, Canadian Centre for Diversity and Inclusion area First Nations, all Advisory Committee member organizations | Ongoing |
| Establish CSWB community engagement plan (PRIORITY |  |  |  |  |  | Municipalities | Advisory Committee members organizations | Ongoing |
| Safe Substance Use |  |  |  |  |  | Pillar Lead - CCAS |  |  |
| Establish Detox Centre (5 yr) and Safe Beds (1 yr) in Red Lake (PRIORITY) |  |  |  |  |  | CCAS | Hospital, OPP, RLIFC | Safe Beds Complete |
| Investigate Substance Intervention Programs in Red Lake and Ear Falls (PRIORITY) |  |  |  |  |  | Family Health Teams | Hospital, OPP, RLIFC, NWHU, Schools, Firefly, RLIFC | Ongoing |
| Develop and implement proactive Situation Table protocols (PRIORITY) |  |  |  |  |  | OPP | CCAS, Hospital, KRRCFS, Firefly | Complete |
| Implement evidence-based prevention planning |  |  |  |  |  | NWHU | KPDSB, RLIFC |  |
| Develop and implement standardized primary assessment and referral protocols/resources aligned with community paramedicine program |  |  |  |  |  | KDSB | Hospital, Paramedicine, OPP, Family Health Teams, LHIN, CCAS |  |
| Establish shared agency training protocols and resources |  |  |  |  |  | KDSB | TBD |  |
| Mental Health |  |  |  |  |  | Pillar Lead – Firefly |  |  |
| Establish Youth Drop In Centre (PRIORITY) |  |  |  |  |  | Firefly | KDSB, Municipalities, RLIFC, OPP, Community Organizations | Complete |
| Establish Safe / Stabilization beds |  |  |  |  |  | CCAS | CCAS, Family Health Teams |  |
| Optimize use of telehealth for psychiatric and support services |  |  |  |  |  | Family Health Teams | Hospital, CCAS, Firefly, LHIN, |  |
| Establish proactive coping support program for families and seniors |  |  |  |  |  | RLIFC | Family Health Teams, Firefly |  |
| Housing |  |  |  |  |  | Pillar Lead – KDSB |  |  |
| Establish affordable, assisted living facility for seniors (PRIORITY) |  |  |  |  |  | Municipalities | LHIN, KDSB, Home for the Aged, Hospital, RLIFC, Cdn Mental Health Assoc. | Ongoing |
| Establish Supportive Youth Housing |  |  |  |  |  | Tikinagan | KRRCFS, RLIFC, Red Lake Emergency Shelter, KDSB |  |
| Establish In-home support services (to enable aging in place) |  |  |  |  |  | KDSB | LHIN, Municipalities, Canadian Mental Health Association |  |
| Assess & forecast need for seniors housing across the full continuum |  |  |  |  |  | LHIN | KDSB |  |
| Assess need and develop plan for affordable multi-unit housing |  |  |  |  |  | KDSB | Municipalities |  |
| Conduct comprehensive review of supports for maintaining tenancy/housing |  |  |  |  |  | KDSB | TBD |  |
| OUR WORK PLAN | 2021 | 2022 | 2023 | 2024 | 2025+ | Working Group |  |  |
|  |  |  |  |  |  | Lead | Advisory Committee Members and other Key Resources (preliminary) | Status |
| Family Environment |  |  |  |  |  | Pillar Lead – RLIFC |  |  |
| Develop and implement community programming & promotion strategy (PRIORITY) |  |  |  |  |  | Municipalities | NWHU, Firefly | Complete |
| Establish coordinated supply chain for family support services |  |  |  |  |  | TBD | KDSB, Family Health Teams |  |
| Expand utilization of Early ON centres |  |  |  |  |  | KDSB | Family Health Teams, School Division, CFS, Tikinagan |  |
| Establish inter/intra community transportation |  |  |  |  |  | KDSB | RLIFC, Tikinagan, KRRCFS, CCAS, NOMA |  |
| Establish partnerships for coordinated pre-natal support |  |  |  |  |  | NWHU | Family Health Teams, NWHU |  |
| Financial Security |  |  |  |  |  | Pillar Lead – Township of Ear Falls Economic Development (year 1) |  |  |
| Improve internet connectivity, speed, and cost |  |  |  |  |  | Municipalities | Northwestern Ontario Municipal Association (NOMA) |  |
| Expand access to adult & continuing education |  |  |  |  |  | KPDSB (School District) | Municipality, RLIFC, RL Adult Ed. Centre, Confederation College |  |
| Establish coordinated food security program |  |  |  |  |  | RLIFC | NWHU, KPDSB |  |
| Coordinate data from school completion programs |  |  |  |  |  | School Division | RLIFC, KDSB |  |
| Connect to/expand local access for Early Childhood Education training |  |  |  |  |  | KDSB | KPDSB |  |
| Coordinate & activate economic development to support diverse local economy |  |  |  |  |  | Municipalities | Chukuni Communities Development Corporation (CCDC) |  |

Legend:  Orange – Priority projects, Grey – Non-Priority Projects, Green – Completed Projects